## Gantt Chart
[8 empty] | LEGENDS: |  | Work Finished |  |  | Assigned to: Lance
[10 empty] | Work In Progress |  |  | Assigned to: Regina
[10 empty] | No Progress |  |  | Assigned to: Liana
[10 empty] | Holiday/No Classes |  |  | Everyone
ID | TASKS | Month 1 | [16 empty] | Month 2 | [29 empty] | Month 3
|  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 7
 | time axis 2022-10-04 to 2022-12-18
1 | Installation and Verification of Necessary Software for Development.
2 | Database
3 | Login Module
4 | Registration Module
5 | Map Module
6 | Listing Module
7 | Space Recording Module
8 | E-Commerce Module
9 | Desktop Dashboard
10 | View Switching (Between Renter and Host)
11 | Account Information Editing
12 | Front-end for Landing Page
13 | Front-end for Login and Registration
14 | Front-end for Map Module
15 | Front-end for Listing Module
16 | Front-end for Space Recording Module
17 | Front-end for E-Commerce Module
18 | Front-end for Desktop Dashboard
19 | Bottom to Top Assessment
20 | System Maintenance